## GII COs 2181
PECONIC PARTIAL RENOVATION (CP 2181)
CHANGE ORDER SUMMARY |  |  | Board of Trustees
2012-10-18 |  |  | Attachment IV
Original Construction Budget |  | 1310000
Original Construction Contracts to Date | 1030131
GII Major Change Order No. 1 | 220000
GII Major Change Order No. 2 | 30661
Pending Change Orders (Approximate) | 2000
Estimated Cost of Project Construction to Date | 1282792 | 1282792
Estimated Project Construction Balance Available |  | 27208
ASBESTOS ABATEMENT (CP 2168)
CHANGE ORDER SUMMARY
2012-10-18
Original Construction Budget |  | 3000000
Original Construction Contracts to Date | 2889671.52
GII Major Change Order No. 2 | 1979
Pending Change Orders (Approximate) | 0
Estimated Cost of Project Construction to Date | 2891650.52 | 2891650.52
Estimated Project Construction Balance Available |  | 108349.48
INFRASTRUCTURE - COLLEGE WIDE (CP 2149)
CHANGE ORDER SUMMARY
2012-10-18
Original Construction Budget |  | 19200000
Original Construction Contracts to Date | 4717073
GII Major Change Order No. 2 | 88807
Pending Change Orders (Approximate) | 0
Estimated Cost of Project Construction to Date | 4805880 | 4805880
Estimated Project Construction Balance Available |  | 14394120
REMOVAL OF ARCHITECTURAL BARRIERS / ADA COMPLIANCE (CP 2127)
CHANGE ORDER SUMMARY
2012-10-18
Original Construction Budget |  | 3000000
Original Construction Contracts to Date | 672259
GII Major Change Order No. 2 | 9875
Pending Change Orders (Approximate) | 0
Estimated Cost of Project Construction to Date | 682134 | 682134
Estimated Project Construction Balance Available |  | 2317866